## Sheet1
# | Name | Type | PIC | Start date | End date | Description | kick-off 1 | completion 1 | Non-negotiable | Complexity | Quick-win | Impact | Prioritas
1.1 | Enhance service excellence | P |  | 2014-03-01 | 2017-03-31 | Establish client tiering for wholesale customers and value chain
1.1.A | Align and map (existing) client tiering | I | Lead :Gaby Valeria Team:Putu Anandika | 2014-12-01 | 2015-02-28 | Single client tiering model across wholesale & map clients (anchors) |  |  | Foundational | 3 - medium | Quick-win | 3 - high | 1
1.1.B | Define service points and formalise and unify SLAs | I | Lead :Gaby Valeria Team:Putu Anandika | 2014-03-01 | 2015-07-31 | Etablish service level by tiers & formalize SLAs (anchors) |  | 1.1.A | N/A | 3 - medium | Pilot | 3 - high | 1
1.1.C | Enhance Service Level | I | Lead :Gaby Valeria, Basu Vitri Manugrahani Team: Tba | 2015-05-01 | 2015-11-30 | Enhance service capabilities accross channels |  |  |  | 3 - medium |  | 2 - Medium | 2
1.1.D | Establish credit analyst team | I | Lead: Kepas Manurung, Tiwul Widiastuti, Titek Setyowati, Sycipto Prayitno Team: Farid Ma'ruf | 2014-10-31 | 2015-10-31 | Create dedicated credit analyst team to free up RM time (pilot) |  | 7.1.A,7.1.B |  | 3 - medium |  | 3 - High | 1
1.1.E | Implement full CST service model | I | Lead :Gaby Valeria Team:Putu Anandika | 2015-01-01 | 2015-10-31 | Migrate clients to full CST model with lead RM |  |  | Foundational | 3 - medium | Pilot | 3 - high | 1
1.1.F | Design and roll out integrated customer portal | I | Lead: Mahesh Ranade Team: Tba | 2016-07-01 | 2017-03-31 | Develop integrated customer portal to improve product delivery |  | 5.1.T | N/A | 4 - high | Pilot | 2 - Medium | 3
1.2 | Develop sector solutions | P |  | 2014-07-01 | 2019-11-30 | Developing and piloting proposition for priority sectors
1.2.A | Wholesale Portfolio Segmentation | I | Lead: Oliver Wyman | 2014-06-01 | 2014-07-01 | Redefine client segmentation: corporate, commercial, MSME |  |  |  | 3 - medium |  | 3 - High | 1
1.2.B | Complete healthcare and port pilot and full roll out | I | Healthcare Lead: Andrianto Wahyu Adi,Arya Suprihadi Team: Sunarto Xie, Dyah Eti Irawati Port Lead: Indarto Pamoengkas Team: Ikhwan M Nasution | 2014-07-01 | 2015-12-31 | Continue existing PCM efforts & launch solutions |  | 8.1.H | N/A | 4 - high | Pilot | 3 - High | 1
1.2.C | Launch Proposition across other sectors: FMCG-F&B, Plantation, Oil&Gas,Goverment,Telco,Building Materials,Infrastructure | I | Sector Solutions Lead: Rustam S. Sirait Team:Tongki Lentari FMCG-F&B Lead: Yusac L Silalahi Team: Tba Plantation Lead: Sucipto Prayitno Team: Nurulloh Proyp Sembodo Oil&Gas Lead: Alexandra Askandar Team: Faiz Firdausi Government Lead :Indarto Pamoengkas Team: Tba Telco Lead: Arya Suprihadi Team: Dyah Eti Irawati | 2014-11-01 | 2019-11-30 | Coordinate, detail & launch sector initiatives across priority sectors | 2.2.A,2.2.B |  | N/A | 4 - high | Pilot | 3 - high | 1
1.3 | Build out sector expertise | P |  | 2015-04-01 |  | Build Self branding as an expert in sectors priorities , including ensuring the competence upgrade
1.3.A | Build out sector branding | I | Lead: Tba (Strategic Marcomm) Team: Ilham Farizal | 2015-10-01 |  | Align branding with sector proposition across priority sectors |  |  |  | 2 - low | N/A | 2 - Medium | 3
1.3.B | Upgrade RM Competency | I | Lead: Anita Widjaja Team: Stefan | 2015-04-01 |  | Upgrade RM skill set according to enhanced RM competency model |  | 1.2 | N/A | 2 - low | N/A | 3 - High | 3
1.3.C | Enhance Sector Information Support | I | Lead :Gaby Valeria Team:Putu Anandika | 2015-07-01 |  | Ensure RM access to internal & external industry knowledge |  |  |  | 3 - medium |  | 2 - Medium | 3
1.4 | Enhance product suite | P |  | 2014-03-01 | 2018-11-30 | Develop propositions related products IWTB , ie SCF , MCM , Trade Fin , Structured Fin , Capital Market , including cross - border offering and FI
1.4.A | Upgrade Trade Finance | I | Lead: Andrianto W Adi Team:Cera Wirastuti | 2014-03-01 | 2015-08-31 | Upgrade SCF platform to meet client functionality needs |  |  | N/A | 3 - medium | Pilot | 2 - medium | 2
1.4.B | Upgrade MCM | I | Lead: Andrianto W Adi Team: Prita Sesanti | 2015-01-01 | 2015-07-31 | Upgrade MCM platform to meet target state PCM functionality |  |  |  | 3 - medium |  | 2 - Medium | 2
1.4.C | Upgrade Trade Finance | I | Lead: Andrianto W Adi Team: Trilaksito Singgih | 2014-09-01 | 2015-11-30 | Enhance service standards & pricing |  |  |  | 3 - medium |  | 2 - Medium | 2
1.4.D | Build out Structured finance | I | Lead: Maqin Norhadi Team: Tba | 2015-03-01 | 2015-12-31 | Build out core project finance offering |  | 6.1.A | N/A | 4 - high | Pilot | 2 - medium | 2
1.4.E | Upgrade Capital Markets offering | I | Lead: Donny Arsal (Mansek) Team: Tba | 2014-09-01 | 2015-12-31 | Build out Capital Market and inbound FDI advisory capabilities |  | 6.3.A | Foundational | 4 - high | Pilot | 2 - medium | 2
1.4.F | Upgrade Cross border offering | I | Lead: Ferry M. Robani (IBFI) Team: Tba | 2014-12-01 | 2015-12-31 | Close critical gaps in intl product offering; tie with MCM replacement |  | 6.3.A | Foundational | 4 - high | N/A | 2 - Medium | 1
1.4.G | Upgrade FICS offering | I | Lead: Ferry M. Robani (IBFI) Team: Tba | 2014-07-01 | 2018-11-30 | Upgrade domestic custody offering & outsourcing capabilities |  |  | Foundational | 3 - medium | N/A | 2 - medium | 2
1.5 | Upgrade CRM and MIS tools | P |  | 2015-01-01 | 2015-07-31 | Upgrade key data infrastructure (CRM & MIS)
1.5.A | Improve data management, capture and access | I | Lead: Mahesh Ranade (IT Application Development) Team: Tba | 2015-01-01 | 2015-07-31 | Ensure data is fit for purpose & captured systematically | 5.2.A |  | N/A | 4 - high | N/A | 3 - High | 2
1.6.B | Upgrade CRM | I | Lead: Mahesh Ranade (IT Application Development) Team: Tba |  |  | Integrate data sources to create 360 degree customer view |  |  |  | 4 - high |  | 3 - High | 2
1.6.C | Upgrade MIS | I | Lead: Mahesh Ranade (IT Application Development) Team: Tba |  |  | Provide single data interface and source of truth across the bank |  |  |  | 4 - high |  | 3 - High | 2
1.6 | Develop relationship pricing | P |  | 2015-01-01 | 2015-12-31 | Develop pricing strategy and policy , including pricing intelligence function
1.6.A | Establish pricing strategy, map clients, and formalise pricing policies | I | Lead: Gaby Valeria Team: I Putu Anandika | 2015-06-01 | 2015-12-31 | High level strategic guidance for pricing decisions & policies |  | 5.5.A | Foundational | 4 - high | Pilot | 3 - High | 1
1.6.B | Establish pricing intelligence function | I | Lead: Andrianto W. Adi Team: Tba |  |  | Establish function to collate & analyze market pricing information |  |  |  | 3 - medium |  | 2 - Medium | 2
1.6.C | Pricing tool review and upgrade | I | Lead: Gaby Valeria Team: I Putu Anandika | 2015-01-01 | 2015-12-31 | Ensure pricing tools are understood, user friendly and fit for purpose |  |  | N/A | 4 - high | N/A | 3 - high | 1
Formulas:
Start date = MIN([Start date, row below]:E8)
Start date = MIN([Start date, row below]:[Start date, row below])
End date = MAX([End date, row below]:F8)
End date = MAX([End date, row below]:[End date, row below])